FOUR-WEEK STUDENT PROJECT DELIVERY PLAN

# SmartBook

Intelligent Resource & Activity Booking Platform

Implementation Plan  ·  Version 1.0

ONE MONTH. THREE DEVELOPERS. ONE WORKING BOOKING FLOW.

October 12 – November 8, 2026

Estimated workload: 15 hours / person / week  |  180 team hours

| TEAM MEMBER | PRIMARY OWNER | CORE RESPONSIBILITY |
| --- | --- | --- |
| Phát | Frontend (FE) | React screens, UI states, API integration, E2E flows |
| Bảo | AI & recommendation | Alternative-slot ranking, FastAPI intent parser, evaluation |
| Huy | Backend (BE) | Spring Boot, PostgreSQL, auth, booking concurrency, deployment |

Project success statement A provider can publish a resource; a customer can search, book, and cancel; the system prevents overselling under concurrent requests and suggests feasible alternatives. Natural-language search assists but never controls booking correctness.

Source basis and change status

Based on Project Research & Feasibility Study v2 (September 2026), SmartBook PRD v2 and SmartBook Technical Design & Project Plan v2 (2 October 2026), plus the latest four-week scope agreed in chat. This short-plan scope is a proposed change to the approved 10-week PRD and needs team sign-off.

PROJECT BRIEF

# 1  Executive decision

Build a web-based Smart Booking MVP for badminton courts and study/studio rooms. Use fixed published time slots with seat capacity (not arbitrary date-range reservations). Prioritize correctness over feature breadth. The plan is structured as four weekly deliverable gates with parallel FE, AI and BE work.

Delivery rule The booking system must work when the AI service is stopped. All capacity checks, validation, authorization and final writes stay in the Java/PostgreSQL core.

## Success outcomes by the end of Week 4

Customer can search and reserve a slot, view history, and cancel a booking.

Provider can create a simple resource/service and publish fixed slots.

50 concurrent one-seat requests to a five-seat slot yield exactly five accepted bookings, with zero overselling.

An unavailable selection returns available alternatives with brief deterministic explanations.

Natural-language intent becomes visible, editable filters; manual search still works if AI is unavailable.

A fresh clone launches with one documented Docker Compose command and seeded demo data.

## Workload and decision owners

| OWNER | ALLOCATION | REVIEW / SECONDARY OWNERSHIP |
| --- | --- | --- |
| Phát · FE | 60 h total · 15 h/week | E2E workflow checks, demo UX, backend endpoint feedback |
| Bảo · AI | 60 h total · 15 h/week | Ranking implementation/test fixtures; reviews data/AI contract |
| Huy · BE | 60 h total · 15 h/week | Database migrations, APIs, concurrency, CI/deployment; reviews FE/AI integration |

## Baseline vs. one-month changes

| PRD v2 baseline (approved) | One-month working scope (proposed deviation) |
| --- | --- |
| 10-week plan with PENDING_PAYMENT holds, expiry and mock payment | 4-week plan with direct CONFIRMED booking and no payment/hold implementation |
| Recurring rules, automatic slot generation, exceptions | Provider manually publishes fixed slots; seed additional ready-made slots |
| Distance/rating/personalized ranking, reviews, notifications | Rank feasible alternatives by time, price and category; no reviews or notifications |
| Two cancellation policies, atomic reschedule | Basic cancellation only; rescheduling deferred to cancel + separate booking |
| Full admin and provider management | Seeded customer/provider accounts; small provider form and limited resource/slot management |

Change control: PRD v2 §15 and Technical Design v2 §21 require a recorded Change Log entry for altered baseline decisions. Until approved, the deviations above are planning proposals—not implemented PRD requirements.

SCOPE FREEZE

# 2  Functional scope

| PRIORITY | INCLUDED IN 4-WEEK MVP | NOT IN THIS RELEASE |
| --- | --- | --- |
| P0 · Must | Login for seeded customer/provider; authorization; resource/service browse and publish | Password reset, detailed admin UI, user preferences |
| P0 · Must | Published fixed-slot calendar; seat-capacity-aware availability | Recurring-weekly schedule engine, midnight-rule expansion, exceptions |
| P0 · Must | Atomic booking; duplicate-submit protection; booking history and cancellation | Mock payment, 10-minute holds/expiry, refunds, reschedule |
| P0 · Must | 409 unavailable response + nearest feasible alternatives | Maps, real-time calendar sync, waitlists |
| P0 · Must | One AI feature: natural-language intent-to-filters parser | Chatbot, RAG, learned personalization, AI-generated availability |
| P1 · If ahead | Venue coordinates / richer time-price explanations | Reviews, notifications, images, dynamic pricing |

Freeze point: end of Week 1. A feature is accepted into the core sprint only if it preserves the Week 2 booking milestone and Week 4 final test buffer.

DESIGN

# 3  Architecture & service boundaries

Use a modular Spring Boot backend and one PostgreSQL database, with a separate small FastAPI parser. React calls only the Spring API. The recommendation algorithm lives inside the Java backend (Bảo owns its implementation and tests), so alternative suggestions never depend on the availability of the Python AI service.

| COMPONENT | STACK | RESPONSIBILITY / OWNER |
| --- | --- | --- |
| Web application | React + TypeScript (Vite) | Phát — customer and provider flows; manual filters; booking feedback |
| Core API | Java 21 + Spring Boot | Huy — auth, CRUD, availability, bookings, validations, error responses |
| Recommendation module | Java package in backend | Bảo — filter feasible candidates, compute rankings, explanation factors; Huy code-reviews |
| Intent parser | Python + FastAPI | Bảo — natural language → typed SearchCriteria; no database or booking access |
| Data layer | PostgreSQL + Flyway | Huy — schema, migrations, transaction and indexed queries |
| Dev & demo | Docker Compose + GitHub Actions | Huy — reproducible launch, CI; all members maintain their test jobs |

## Main runtime sequence

Search: React → GET /services and /services/{id}/slots → Spring reads available capacity from PostgreSQL → React renders slots.

Booking: React → POST /bookings with Idempotency-Key → Spring locks and validates → one DB commit → returns CONFIRMED or 409 with alternatives.

AI search: React → POST /search/parse → Spring → FastAPI → typed JSON filters → Spring validates → React lets customer inspect/edit filters → normal search.

Failure: if FastAPI times out or returns invalid JSON, Spring sends a safe parse error; React presents manual filters without losing the query.

## Minimum database tables

| TABLE | ESSENTIAL FIELDS | NOTES |
| --- | --- | --- |
| users / user_roles | id, email, password_hash; role | Seeded demo accounts; server validates permissions |
| services / resources | provider_id, category, price_vnd, price_unit; capacity | Services carry price policy; resources carry default capacity |
| slots | id, resource_id, starts_at, ends_at, capacity, status | One fixed bookable unit; index resource_id + starts_at |
| bookings | user_id, slot_id, party_size, status, total_price_vnd, created_at | Direct CONFIRMED or CANCELLED; price snapshot; only active bookings consume seats |
| idempotency_keys / booking_events | user_id, key, request hash; status changes | Avoid duplicate submit; explain history |

Source-derived invariants retained: fixed generated/published slots, seat capacity, per-person vs per-booking prices in integer VND, UTC instants and Asia/Ho_Chi_Minh venue times. The manual-slot creation mechanism is a four-week simplification.

DELIVERY ROADMAP

# 4  Four-week timeline

| WEEK / DATES | PHÁT — FE | BẢO — AI / ALGORITHM | HUY — BE | DEMO / EXIT GATE |
| --- | --- | --- | --- | --- |
| W1 Oct 12–18 | React skeleton; login/search mock UI; shared DTO types | 30 NL test phrases; parser JSON schema; ranking cases | Spring skeleton; Flyway/DB schema; auth; contracts | Mock UI + runnable API/DB; route and DTO agreement |
| W2 Oct 19–25 | Search/results/details/slot UI connected to API | Java candidate ranking + alternatives tests | Services/slots + atomic POST /bookings; concurrency test | Customer can book; 50-request stress check cannot oversell |
| W3 Oct 26–Nov 1 | Booking status/cancel; conflict suggestions; AI search UI | FastAPI parser; accuracy tests; BE adapter support | Cancellation; idempotency; AI adapter; 409 alternatives | Full path: text → filters → find → book/cancel → conflict alternative |
| W4 Nov 2–8 | E2E, polish, responsive UX, demo script | Parser/ranking evaluation, fallback checks, report | CI, deploy, security/concurrency regression, API docs | Fresh clone starts; all hard gates pass; presentation ready |

Critical path: schema/API agreement (W1) → capacity-safe booking (W2) → FE/AI integration (W3) → hardening (W4). Target no new features after 1 November.

EXECUTION

# 5  Owned task backlog

## Phát — Frontend, 60 estimated hours

| TASK / WEEK | HRS | IMPLEMENTATION DELIVERABLE | ACCEPTANCE CONDITION |
| --- | --- | --- | --- |
| FE-01 · W1 | 12 | React/TypeScript setup, navigation, auth state, typed API client; mocked screens | Can navigate login → search → service detail with fixtures; loading/error states visible |
| FE-02 · W2 | 16 | Search filters, service cards/detail, fixed-slot picker and booking request | Consumes real /services and /slots; disables impossible party sizes; shows server errors |
| FE-03 · W3 | 18 | Booking status/history, cancellation, 409 alternatives, NL search panel | End-to-end success and unavailable paths; parsed fields editable before search |
| FE-04 · W4 | 14 | E2E tests, responsiveness, UX fixes, short demo and screenshots | Primary flow passes in browser, 390px mobile viewport usable, no blocked critical actions |

## Bảo — AI & Algorithms, 60 estimated hours

| TASK / WEEK | HRS | IMPLEMENTATION DELIVERABLE | ACCEPTANCE CONDITION |
| --- | --- | --- | --- |
| AI-01 · W1 | 12 | Typed intent response schema; 30-query evaluation file; 20 ranking scenarios | Each example has an expected output; ambiguous fields represented as missing, not invented |
| AI-02 · W2 | 16 | Java RecommendationStrategy scoring/time-price matching, Top-K, deterministic explanations | Ranks only eligible capacity-feasible slots; returns ≥3 where seeded; JUnit scenarios pass |
| AI-03 · W3 | 18 | FastAPI /parse parser; JSON validation, bounded timeout, error handling | 30-query exact-match target ≥85%; no booking or SQL access; Spring adapter accepted |
| AI-04 · W4 | 14 | Accuracy review, prompt-injection and AI-offline fallback tests, report subsection | Published confusion examples, pass/fail count, fallback works with AI container stopped |

## Huy — Backend, 60 estimated hours

| TASK / WEEK | HRS | IMPLEMENTATION DELIVERABLE | ACCEPTANCE CONDITION |
| --- | --- | --- | --- |
| BE-01 · W1 | 14 | Spring Boot foundation; Flyway tables; seeded accounts; JWT login; OpenAPI contracts | Fresh database migrates; login, role checks and GET /health pass |
| BE-02 · W2 | 20 | Service/slot endpoints; seat counting; transaction-safe POST /bookings | No oversell under 50 parallel requests at capacity 5; rejects self-overlap |
| BE-03 · W3 | 16 | Booking list/cancel; idempotency replay; 409 alternatives; parser proxy | Cancellation frees capacity; repeat key makes one booking; correct error codes |
| BE-04 · W4 | 10 | CI/Compose, security negative tests, seed dataset, README & API examples | All services start from clone; tests green; no secrets committed |

Ownership boundary Every item has one accountable owner. Phát can use mocks while Huy completes APIs. Bảo owns algorithm code/tests in the backend repo; Huy reviews booking-related safety. Huy owns DB changes; Phát and Bảo review API and data changes before merge.

INTEGRATION

# 6  Contracts to freeze in Week 1

| ENDPOINT | INPUT / RESPONSIBILITY | OUTPUT / REQUIRED BEHAVIOR |
| --- | --- | --- |
| POST /auth/login | email + password | JWT + role set; seeded customer/provider accounts |
| GET /services | category, date, partySize, maxTotalPrice | Paged service list; no internal auth data |
| GET /services/{id}/slots | from, to, partySize | Fixed slots + seatsRemaining and totalPriceVnd |
| POST /providers/services | Provider JWT; service + resource + slots (simple create flow) | Created IDs; refuses non-provider and non-owner |
| POST /bookings | slotId, partySize + Idempotency-Key header | 201 CONFIRMED; 409 UNAVAILABLE/CONFLICT with alternatives |
| GET /bookings/me | Customer JWT | Own bookings and statuses |
| POST /bookings/{id}/cancel | Owner JWT | Cancelled booking and released capacity; 403 otherwise |
| POST /search/parse | text, timezone, nowInstant | Validated typed filters or 422/503; never modifies bookings |

## Example booking error contract

HTTP 409  •  { "code": "UNAVAILABLE", "message": "Not enough seats", "details": { "seatsRemaining": 0 }, "alternatives": [{ "slotId": 104, "score": 0.86, "reason": "Same venue, 60 minutes later" }] }

For P0, the exact field names and UTC timestamp format are frozen in /docs/api/openapi.yaml on W1 Friday. FE branches on machine-readable code, not human message. No client-supplied price or userId is trusted.

ENGINEERING

# 7  Correctness & algorithm design

## Transactional seat allocation — Huy

Validate partySize, slotId and authorization, and check the idempotency key (userId + key + request hash).

In a PostgreSQL transaction, lock the requesting user row first, then the requested slot row (consistent lock order for booking and cancellation).

Check slot OPEN and future; compute consumed seats from CONFIRMED bookings; reject if consumed + partySize > slot.capacity.

Under the same user-row lock, check whether the user already owns a CONFIRMED booking whose slot overlaps [starts_at, ends_at). Adjacent half-open intervals are allowed.

Calculate and freeze total price (PER_PERSON × partySize; PER_BOOKING × 1), insert CONFIRMED booking and event, persist idempotency result, commit.

On capacity rejection, return 409 and independently query feasible alternatives; re-check an alternative at the next booking attempt.

The two-lock recommendation (user row followed by slot row) adds serialization for same-user bookings across different slots. It is a proposed four-week safeguard; review and test consistently with the approved Technical Design v2 lock sequence before implementing.

## Acceptance tests for the transaction

| CASE | EXPECTED RESULT |
| --- | --- |
| 50 different customers simultaneously request 1 seat each; only 5 are free | Exactly five successful bookings; no negative remaining seats and no server 500s |
| One customer concurrently books overlapping slots on two resources | At most one succeeds; loser gets CONFLICT |
| Same Idempotency-Key submitted twice with same body | One booking; replay returns original booking |
| Same Idempotency-Key submitted with changed body | 409 IDEMPOTENCY_MISMATCH; no extra booking |
| Cancel confirmed booking while another request is waiting | Correct final seat count; transaction ordering avoids overselling |

## Deterministic alternatives — Bảo

Filter to published slots with enough remaining seats and valid date/time/cost constraints; then rank the eligible candidates. For this four-week MVP use score = 0.55 × timeFit + 0.30 × priceFit + 0.15 × categoryFit, all normalized to [0,1]. Return the best three with rule-based explanations. No suggestion is a guarantee of future availability.

This simplified weighting replaces PRD v2’s five-factor demonstration formula (time 0.30, preferences 0.25, price 0.20, distance 0.15, rating 0.10). Mark this deviation in the Change Log. Distance and ratings can be restored after the core demo is stable.

## AI parser — Bảo

Example text: “Badminton tomorrow evening for 4 under 300k.” The Python service returns only structured fields such as category, date, timeFrom/timeTo, partySize and maxTotalPriceVnd. “Tomorrow” resolves using the supplied clock and venue timezone (Asia/Ho_Chi_Minh for seed data). Spring validates every field before search.

Failure behavior: parser timeout / malformed JSON / unknown category → 422 or 503 with a manual-search path; no fabricated slot and no booking action.

Evaluation: 30 fixed user utterances, ≥26/30 exact matches for the selected critical fields; log the misses and never present accuracy as trained ML performance.

Security: parser has no DB credentials, booking API access, tool execution, or field to request automatic confirmation; prompt-injection cases must have no side effects.

RELEASE QUALITY

# 8  QA, deployment & evidence

## Minimum quality gates

| LAYER | OWNER | TEST / PROOF |
| --- | --- | --- |
| Unit & service | Huy, Bảo | Price units, overlap predicate, capacity, ranking and explanations, input validation |
| API & authorization | Huy | Login failure, provider-only mutation, customer cannot cancel/read another booking |
| Concurrency | Huy | 50 parallel requests for 5 seats; repeat 3 runs; plus same-user overlap race |
| AI evaluation | Bảo | 30 parse queries, 20 ranking scenarios, AI-offline fallback, injection case |
| Browser E2E | Phát | Search → detail → book → history → cancel; unavailable → alternatives |
| Deployment smoke | Huy + all | docker compose up --build, seeded users, seeded 3-alternative scenario |
| CI | All contributors | Each PR runs Java, Python and FE checks; backend DB tests enabled |

## Security / operations checklist

Passwords hashed with BCrypt. JWT permissions checked server-side; owners validated on each provider/booking route.

Use Flyway migrations; parameterized queries; sensible field bounds (partySize 1–20, positive capacity, future slots).

Credentials live in environment variables; commit .env.example without secrets. Never expose SQL errors or hashes.

Use UTC-aware timestamptz for slot starts/ends, render venue-local times, and compare intervals as half-open ranges.

Keep a deterministic seed dataset, a short failure-free screen recording as demo backup, and a brief known-limitations page.

FINAL DELIVERY

# 9  Risks, cut order & demo

| RISK | EARLY INDICATOR | MITIGATION / OWNER |
| --- | --- | --- |
| Booking race not solved | W2 concurrency test flaky | Huy: prioritize transaction first; postpone provider polish |
| Provider UI takes too long | W2 no stable publish screen | Phát/Huy: seed slots; retain minimal provider creation API |
| AI availability/cost issue | W3 parse returns inconsistent JSON | Bảo: schema validation and manual-filter fallback; record demo fixtures |
| Integration mismatch | UI blocked on endpoint changes | Freeze OpenAPI W1; Phát mocks exact contract; daily 10-minute sync |
| Uneven team workload | One owner blocked for >1 day | Move tests/fixtures; retain clear single owner per task |
| Deployment failure | Docker bootstrap fails on clean machine | Huy: build Compose W1, rehearse fresh-clone launch in W2 |
| Scope creep | Requests for maps/reviews/payment | Only consider after 4-week acceptance gates are met |

## 5-minute final demonstration

| TIME | SHOW | ACADEMIC POINT |
| --- | --- | --- |
| 0:00–0:45 | Provider/resource and published slots | Domain relationships + database |
| 0:45–1:45 | Customer filters, selects and confirms booking | End-to-end integration and price snapshot |
| 1:45–2:45 | 50-request race; one unavailable request and alternatives | Transactions, concurrent seat integrity and Top-K |
| 2:45–3:45 | Natural-language request → validated editable filters | AI assistance with deterministic search |
| 3:45–4:30 | Switch AI off; search still succeeds; cancel booking | Resilience and capacity release |
| 4:30–5:00 | Show JUnit/pytest/E2E results and architecture | Measured tests and layered design |

## Final artifacts due Sunday, November 8

Source repository with frontend/, backend-java/, ai-service-python/, migrations, tests and Docker Compose.

README with setup, seeded credentials and exact demo commands; OpenAPI schema and sample request/response bodies.

Architecture diagram, reduced ERD, one booking sequence diagram and explicit scope-deviation Change Log.

Test evidence: concurrency log, E2E result, parser accuracy (numerator/30), ranking fixture report and known limitations.

Slide deck / short report and 5-minute demo script with fallback recording.

## Sign-off items (complete at Week 1 kickoff)

| DECISION | PROPOSED ANSWER | APPROVAL |
| --- | --- | --- |
| Project duration | 4 weeks, Oct 12–Nov 8, 2026 | Phát / Bảo / Huy: __________ |
| Booking state | Direct CONFIRMED; defer payment + holds | Phát / Bảo / Huy: __________ |
| Schedule scope | Provider publishes fixed dated slots | Phát / Bảo / Huy: __________ |
| Time budget | 15 h/person/week = 180 team h | Phát / Bảo / Huy: __________ |

Any lecturer requirement that mandates the original PRD payment/hold/schedule capabilities requires re-estimation and cutting other items. Record the decision before Week 2.

APPENDIX

# 10  Source references & provenance

The following uploaded materials were used as source baseline (all provided by the project owner):

Project Research & Feasibility Study v2 — September 2026; Smart Booking concept, student-size team fit, architecture and original 12-week guide.

SmartBook Product Requirements Document v2 — 2 October 2026; fixed slots and capacity (D-03/D-04), price units, timezone rules, holds and payment state machine.

SmartBook Technical Design & Project Plan v2 — 2 October 2026; Spring/PostgreSQL architecture, migrations, booking transaction, API/error model, ranking, AI design and original 10-week delivery plan.

smart-booking-main.zip — inspected October 10, 2026. Contains README.md, PRD v1/v2 and Technical Design v1/v2 (plus .gitignore); no application source files in this archive.

Planning assumptions and estimates added in this document (not claimed as existing implementation): four-week schedule, 15 hours/person/week, direct-confirm booking, simplified manual slot publishing, reduced ranking weights, named ownership, task hours, tests and target dates.